## Sheet1
| Panel 1: Welcome | Panel 2: The Map | Panel 3: Statistics | Panel 4: Challenge(?)
Chris
Hasan
Shahriah
Talal
Panel 1 breakdown | Create the GUI window | Create Labels for the instructions and welcome | From and To dropdown boxes for dates | Check date validity and within suitable range for data | Buttons disabled until valid date is entered | Optional: Unit testing for panel 1
Panel 2 breakdown | Create the GUI panel | Create Shape objects for each borough either using reference picture or out own design | Turn shapes to buttons | Shapes change colour depending on covid death rate | Each shape has its own ID for statiscics processing | Unit testing to check everything works | Create new window for each borough | Window should have borough in the title + all statistics shown on task sheet | Drop down menu to reorder the data, sorting by column
Panel 3 breakdown | Create the GUI panel | Cycleable from Panel 2 | embedded panel within 3rd panel, own navigation arrows | 5 different panels from task sheet with calculated data | Processing class linked to panel. Handles all the 5 required stats
Panel 4 breakdown | Create the GUI window | Leaderboard system, top borough for each column
Deadlines | By 21/03: Panel 1 drafted with code, started/ midway into panel 2 with some code/designs done |  | By 24/03: Panel 2 drafted completely with panel 3 mostly done/ done completely |  | By 25/03 One person(s) draft some unit tests for atleast 1 class, can be done throughout development |  | By 27/03: Panels 1 - 3 should be fully complete, if done beforehand then all 4 members work on panel 4 together |  | By 28/03: report for the coursework